# ORCS Site-Specific Integration

Midwest-Optimized Module Combinations & Regional Opportunities

Atlas Lattice Foundation | April 2026

# 1. Climate-Specific Deployment Clusters

The 40-module inventory is not deployed uniformly. Six climate-specific clusters provide operators with an actionable starting point based on site characteristics.

| Cluster | Core Modules | Archetype | Best Regions |
| --- | --- | --- | --- |
| Agricultural (rural) | M1.3 + M1.1/M1.2 + M4.5 + M6.4 | WDC Japan model | Midwest US, Northern Europe, Rural Japan |
| Municipal (urban) | M1.4 + M4.1 + M6.3 + M6.4 | Korean reciprocity | Seoul, Stockholm, Vancouver, Navi Mumbai |
| Arid | M2.1 + M2.3 + M3.7 + M5.5 + M4.8 + M6.1 | Desert deployment | Phoenix, Dubai, Guizhou, North Africa |
| Monsoon | M4.4 + M4.3 + M4.5 + M1.4 + M6.3 | Tropical deployment | India, Philippines, Southeast Asia |
| Temperate | M2.1 + M2.4/M2.5 + M3.5 + M4.2 + M4.6 | Standard hyperscale | US East, Western Europe, Japan |
| Coastal | M1.5 + M2.1 + M1.3 + M6.4 | Shore deployment | Finland, Singapore, Ireland |

# 2. Indiana / Midwest Optimization

Indiana falls into the Agricultural + Temperate overlap — the most favorable combination for regenerative infrastructure. The state offers high humidity (vapor recovery), cold winters (waste heat demand), abundant farmland (CEA partnerships), and moderate water stress (not crisis-level, but enough to motivate action).

## 2.1 Recommended Module Stack for Node Zero

| Priority | Module | Rationale for Indiana | Timeline |
| --- | --- | --- | --- |
| Immediate | M2.3 Raised supply air temp | Free efficiency gain, ASHRAE compliant | 0–6 months |
| Immediate | M5.1 IoT leak detection | Low cost, immediate water savings | 0–6 months |
| Immediate | M3.7 Precision humidity zoning | Eliminate unnecessary humidification | 0–6 months |
| Near-term | M2.1 Hybrid wet-dry cooling | Core architecture for seasonal switching | 6–12 months |
| Near-term | M4.2 Rainwater harvesting | 38–42" annual rainfall, reliable supply | 6–12 months |
| Near-term | M3.1 Electrolytic scale control | 10x cycles of concentration | 6–12 months |
| Medium-term | M2.4 Direct-to-chip liquid cooling | High-density rack support | 12–24 months |
| Medium-term | M1.1 Vapor recovery (retrofit) | 65–80% RH = excellent recovery | 12–24 months |
| Medium-term | M4.1 Greywater integration | Municipal partnership | 12–24 months |
| Keystone | M1.3 CEA thermal offtake | Flips to net-positive; 85% farmland adjacency | 18–36 months |
| Advanced | M1.7 ATES | Glacial till aquifer, needs geological survey | 24–48 months |
| Advanced | M6.3 Municipal reciprocity | Requires utility commission engagement | 24–48 months |

## 2.2 Local Agricultural Integration Opportunities

Indiana's agricultural landscape provides immediate partnership opportunities. The state ranks 5th nationally in total agricultural output, with strong cooperative infrastructure. Specific opportunities include:

Greenhouse tomato and leafy green production using waste heat (replacing natural gas heating, which accounts for 30–40% of greenhouse operating costs). Aquaculture integration following the White Data Center model (tilapia, catfish suited to Indiana climate). Mushroom cultivation using lower-grade waste heat (55–65°F range). Hemp fiber processing using thermal energy for drying operations.

## 2.3 Water Efficiency Projections for Indiana

| Scenario | Modules Deployed | Water Reduction | Watershed Days | Timeline |
| --- | --- | --- | --- | --- |
| Baseline | None | 0% | 0 | Current |
| Phase 1 (Quick Wins) | M2.3 + M3.7 + M5.1 | 15–25% | 0 (still consuming) | 6–12 months |
| Phase 2 (Core) | Phase 1 + M2.1 + M3.1 + M4.2 | 55–70% | ~100 | 12–24 months |
| Phase 3 (Integration) | Phase 2 + M1.1 + M4.1 + M1.3 | 90–110% | +300–365 | 24–36 months |
| Phase 4 (Optimization) | Phase 3 + M1.7 + M6.3 | >110% | +365 sustained | 36–48 months |

# 3. AWS Regional Mapping

For Amazon/AWS specifically, the ORCS module clusters map to existing AWS regions as follows:

| AWS Region | Climate Cluster | Priority Modules | Unique Opportunity |
| --- | --- | --- | --- |
| US-East-1 (Virginia) | Temperate/Agricultural | M1.3, M4.1, M6.3 | Chesapeake Bay restoration ($1.8B federal) |
| US-West-2 (Oregon) | Temperate | M1.3, M4.2, M6.4 | Columbia River Gorge agricultural thermal |
| EU-West-1 (Ireland) | Coastal/Temperate | M1.5, M1.3, M6.4 | Peat bog restoration via thermal management |
| AP-Southeast-1 (Singapore) | Coastal/Monsoon | M1.5, M4.4, M4.3 | Urban agriculture, monsoon harvesting |
| US-East-2 (Ohio) | Agricultural/Temperate | M1.3, M4.2, M2.1 | Midwest farming partnerships |
| AP-Northeast-1 (Tokyo) | Temperate | M1.3, M1.6, M4.2 | Snow cooling + aquaculture (WDC model) |